## Sprint Retrospective
Sprint Retrospective |  |  |  | Guidelines
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints.
Example : All tasks were completed on time. Team communication was seamless. | Requirements changed mid-sprint. | Plan for a buffer to handle scope changes. | Set stricter deadlines for finalizing requirements. | Example
Real-time CRDT sync via Yjs integrated flawlessly with the Monaco Editor, providing <50ms latency across test regions. Supabase Row-Level Security effectively blocked unauthorized room access in all test scenarios, validating the zero-trust architecture. | AI Agent (Qwen2.5) occasionally returned raw markdown blocks instead of pure JSON, causing the 'aiAgent.ts' parser to fail. Memory consumption spiked slowly when multiple large files were kept open simultaneously due to Yjs CRDT history bloat. | Implement a more aggressive regex or a structured output parser for the HuggingFace API response to strip markdown wrappers natively. Add automated state-vector garbage collection for Yjs documents to prevent memory leaks during extended sessions. | Update 'aiAgent.ts' with a regex-based fallback parser to extract JSON blocks reliably before the next sprint review. Research Yjs state-vector optimization and implement a periodic commit to Supabase to clear memory.